#### Risk Management Plan

# 2011 Oceania and Australian Championships

7-9 October 2011

## Background

This plan describes risks to competitors, which may be encountered during the orienteering events comprising the 2011 Oceania and Australian Championships as listed below, and which may require the assistance of parties external to Orienteering ACT (OACT) (e.g. Emergency Services).  It does not cover risks that might be encountered by competitors outside of their attendance at the actual events (e.g. whilst participating in other activities not organised by OACT), during the period in which they are visiting Cooma for this carnival, travelling between the events, or encountered at accommodation, which they have arranged independently.

St John Volunteers will provide emergency First Aid facilities at each event.

## Insurance

These events are covered by Sportscover Australia Pty Ltd organised by Orienteering Australia, Certificate # 22939b, Policy # PMEL99/0060397 (expires 31/1/12).

## Event Details

This plan relates to the following orienteering events –

Event 1

Friday 7 October 2011: Oceania Sprint Distance Championships, Gaerloch, Countegany NSW, Silva National Orienteering League Race # 15 and World Ranking Event.

Event 2

Saturday 8 October 2011: Australian Long Distance Championships, Gaerloch, Countegany NSW, with some courses entering part of Badja State Forest, Silva National Orienteering League Race # 16 and World Ranking Event.

Event 3

Sunday 9 October 2011: Oceania Relay Championships, Gaerloch, Countegany NSW, Silva National Orienteering League Race # 17.

## Risk Identification

The risks identified in this plan are of three types:

1.	Risks to competitors or officials participating in the event.

2.	Risks to the successful conduct of the event itself.

3.	Risks to outside parties (e.g. landholders, the general public), affecting either person or property.

Potential risks, which are commonly encountered, are listed in the following table under these three types, together with means of addressing them.  This table also includes columns for assessing the likelihood and seriousness of each risk at the venues to be used, taking account of the time of the year when the event is scheduled.

## Assessment Guidelines

The likelihood and seriousness (consequence) of each risk are be assessed using a numerical scale where 1 = lowest and 5 = highest.  The following examples are indicative of how these numerical assessments should be applied.

Likelihood

| Rating | Scale | Criteria |
| --- | --- | --- |
| 1. | Remote | a. Would only occur in highly exceptional circumstances. b. An extremely remote chance of an occurrence. |
| 2. | Unlikely | a. Not likely to occur. b. A small, but remote chance of occurrence due to the circumstances or situations that could arise. |
| 3. | Possible | a. Likely to occur at least once, but not expected to occur much more than this. |
| 4. | Likely | a. Likely to occur more than once, but not an ‘everyday’ occurrence. b. Preconditions will arise at times. |
| 5. | Almost Certain | a. Will occur. b. Circumstances are likely to arise often throughout the period which will provide the opportunity for the crystallisation of the risk. c. Expect frequent/ regular occurrences. |

Seriousness (Consequence)

| Rating | Description | Criteria |
| --- | --- | --- |
| 1. | Insignificant | a. no injuries or fatalities; b. little community disruption; c. no environmental or other damage; or d. no significant effect on event. |
| 2. | Minor | a. small number of injuries; b. no fatalities; c. only first-aid required; d. some environmental or other damage (but not lasting); or e. competitors’ enjoyment of event reduced. |
| 3. | Moderate | a. hospital treatment required; b. no fatalities; c. some community inconvenience; d. some environmental damage (small long-term effect); e. other damage; f. major disruption to event or courses cancelled; or g. cancellation of minor event. |
| 4. | Major | a. extensive injuries; b. significant hospitalisation; c. some services unavailable; d. extensive environmental damage (long term affect); e. other extensive damage; f. some community displacement; or g. cancellation of major event. |
| 5. | Severe | a. fatalities; b. injuries and extended hospitalisation periods; c. widespread community displacement; d. extensive and widespread damage; e. significant short or long term environmental damage. |

As a rough guide, if the product of the likelihood and seriousness ratings is 8 or more (eg 4 x 2 or 3 x 3), particular attention should be paid to reducing the risks.  All risks, however, should be managed through risk control measures as far as practicable.  Some risks may be affected by weather or other conditions prevailing on the day of the event, and should be reviewed in this context.

## Evaluation and Monitoring

Should an accident or other incident occur during an event, the event controller should report to the OACT with respect to:

(a)	whether the risk was anticipated; and

(b)	what actions were taken to control the risk.

If necessary, the risk management plan will be reviewed to reflect the additional risk factor or further actions for controlling.  The risk management plan should therefore be treated as dynamic and subject to continuous refinement.

## Risk Register

The following checklist identifies risk control measures relevant to these events.  The likelihood and seriousness of each risk has been rated using a numerical scale (1 = lowest, 5 = highest).  The higher these ratings, the greater priority has been given to controlling the risk.

| Nature of risk | Likeli-hood | Serious- ness | Risk control measures | Check |
| --- | --- | --- | --- | --- |
| A. Risks to competitors or officials Minor injuries to competitors (e.g. grazes, sprains) | 4 | 2 | 1. First aid kit available at assembly area. 2. St John’s Ambulance to attend all events 3. List of qualified first aiders available to organiser. 4. Participants to acknowledge the risks associated with orienteering during entry process. |  |
| Major injuries to competitors (e.g. broken limb) | 2 | 3 | 1. Stretcher available at assembly area. 2. Inform ACT Ambulance Service of event locations and details before the event. 3. Mobile phones and satellite phone available at each event. 4. Arrangements available for emergency access to course area (e.g. keys to locked gate, maps showing access routes). 5. Competitors should be advised to carry a whistle to assist in attracting attention in the event of injury. 6. Participants to acknowledge the risks associated with orienteering during entry process. Note: The rules of orienteering require competitors to abandon their course and assist an injured competitor if necessary. |  |
| Attack by wild animals (e.g. snakes, wild pigs, wild dogs) | 2 | 4 | As for major injuries to competitors. |  |
| Accidents due to fixed hazards (e.g. cliffs, deep rivers, mineshafts). Specific hazards identified are listed below. | 2 | 4 | 1. Courses set to avoid hazardous areas. 2. Hazards marked on maps. 3. Hazards taped in terrain. 4. Warnings issued to competitors during start briefing and in event program. 5. Participants to acknowledge the risks associated with orienteering during entry process. |  |
| (a) Accidents due to cliffs and steep rock faces. | 1 | 4 | 1. Courses set to avoid large cliffs. 2. Competitors issued warning during start briefing. |  |
| (b) Accidents due to fence crossings. | 2 | 2 | 1. Provide adequate fence crossings marked on map and in terrain. 2. Competitors notified of crossing points during start briefing and in event information. |  |

| Nature of risk | Likeli-hood | Serious- ness | Risk control measures | Check |
| --- | --- | --- | --- | --- |
| Accidents due to variable hazards affected by weather (e.g. slippery wet rocks or logs, flooded creeks). Specific hazards identified are listed below. | 4 | 2 | 1. Warnings issued to competitors during start briefing. 2. Safe crossing points installed (e.g. temporary bridges) or taped. |  |
| (a) Accidents due to wet logs. | 2 | 3 | 1. Competitors issued warning during start briefing in case of rain. |  |
| (b) Accidents due to falling trees in case of high wind. | 1 | 4 | 1. Competitors issued warning during start briefing in case of high winds. 2. Cancellation of event in case of severe weather warning issued by Bureau of Meteorology. |  |
| Major hazard requiring evacuation of competitors (e.g. bushfire or fire in assembly area) | 1 | 5 | 1. Inform relevant authorities of location prior to event 2. Hold contact details for relevant authorities at arena 3. Ensure car parking arrangement allows for evacuation within 30mins. |  |
| Traffic accidents at road crossings on course | 2 | 3 | 1. Courses set to avoid road crossings where possible. |  |
| Traffic accidents at assembly/ parking area | 2 | 2 | 1. Assembly/ parking area located away from heavily trafficked roads. 2. Signs to warn traffic erected on roads (or traffic marshals in position). |  |
| Competitors suffer dehydration/ hyperthermia in hot weather | 2 | 2 | 1. Start times scheduled between 9:00 am and 12:30 am for all events except Sprint event. 2. Ample water supplied at assembly area, at start and on courses. 3. Warnings issued to competitors during start briefing in case of hot weather. |  |
| Competitors suffer hypothermia in cold weather | 2 | 2 | 1. Locate start and assembly area in sheltered location or erect shelter for competitors. 2. Warnings issued to competitors during start briefing in case of extremely cold weather. |  |
| Competitors suffer excessive sun exposure | 3 | 2 | 1. Start times scheduled in the morning for all events except Sprint event. 2. Sunscreen available to competitors at assembly area. |  |
| Transmission of blood-borne diseases | 2 | 3 | 1. First aid officials supplied with disposable gloves. 2. Control card/map collectors supplied with disposable gloves. 3. Contaminated maps and control cards separated from main collection. |  |
| Transmission of saliva-borne diseases (e.g. through shared drinking cups) | 2 | 2 | 1. Adequate cups supplied at finish, start and drink controls, and receptacle provided for used cups. |  |
| Competitors seriously lost or overdue necessitating a search | 2 | 3 | 1. Course closing time advised to all competitors. 2. Safety directions (bearing or description) advised to inexperienced competitors. 3. Maps available of area surrounding competition area, including information on vehicular access. 4. Adequate number of fit persons available to assist with search at end of event if required. 5. Search plan developed, including recall arrangements, before any major search commences (see Search and Safety Manual for further details). 6. Telephone number for emergency services available at assembly area, together with mobile phone and satellite phone. |  |
| Fire in the assembly area due to malfunction in catering equipment | 1 | 4 | 1. Caterers required to provide fire extinguishers. 2. Emergency evacuation plan in place to evacuate all competitors within 30 minutes. |  |
| Nature of risk | Likeli-hood | Serious- ness | Risk control measures | Check |
| B. Risks to conduct of event Access to event area prevents by seasonal conditions (e.g. flooding, snow, high wind) | 2 | 3 | 1. Contingency plan developed to switch any event to an alternative area at short notice or cancel the event. |  |
| Permission to use area withdrawn by landholder/manager | 2 | 3 | 1. Maintain effective and regular liaison with landholder/ manager. 2. Ensure access arrangements are agreed and understood well in advance of event. 3. Contingency plan as noted above. |  |
| Conflict with other uses of area (e.g. shooting, archery, motorsport) | 2 | 3 | 1. Confirm no likelihood of conflict with landholder/ manager. 2. Contact other known regular users of area if necessary. |  |
| Competitors have difficulty finding assembly area | 2 | 2 | 1. Provide detailed and accurate written instructions prior to event. 2. Provide clear signage along route to assembly area. |  |
| Event disrupted by extreme weather, e.g. wind, snow, heavy rain | 3 | 3 | 1. Event scheduled to avoid high risk periods. |  |
| Event cancelled due to total fire ban. | 1 | 5 | 1. Contingency plan as noted above. |  |
| Courses cancelled due to technical mistakes or deficiencies | 3 | 3 | 1. Technical planning of events subject to independent review by controller (see controller manuals etc. for details). 2. Suitably experienced course planners and organisers appointed. |  |
| Theft of controls during or immediately prior to event | 2 | 3 | 1. Controls sited in inconspicuous locations as far as practicable. 2. Controls checked by early runners from organising team (or other officials). |  |
| Failure of computers | 2 | 2 | 1. Computer systems (hardware or software) tested under event conditions prior to event. 2. Backup computer available, if practicable. 3. Alternative manual system and personnel to use it available. |  |
| Failure of electronic punching/ timing units | 2 | 2 | 1. Manual punches on all control stands, with punch boxes on maps and competitors briefed with respect to alternative punching. 2. Multiple electronic punches available for clear, check, start and finish. |  |
| Mistakes in ‘final’ results | 2 | 3 | 1. Manual checking and calculations should be double-checked. 2. Independent timing system (e.g video recorder) available for checking finishing order/ times (for major events). |  |
| Withdrawal of key officials due to excessive demands | 2 | 3 | 1. Workload reduced by some routine tasks (e.g. obtaining permission from government agencies, results processing, publicity, banking) handled by other officers. 2. Supporting officials organised through clubs or program co-ordinator. 3. Controller responsible for monitoring workloads and suggesting action if workloads become excessive. |  |
| Withdrawal of key official due to illness or injury | 2 | 3 | 1. Assistant/ deputy appointed to work with each key official and take over if necessary. |  |
| Equipment items not brought to event | 2 | 2 | 1. Develop equipment checklists for all events. 2. Identified person confirms responsibilities for bringing equipment (incl maps) to event. |  |
| Completion of event delayed by late return of competitors | 3 | 2 | 1. Course closing time advised to all competitors. 2. Late starters may be restricted to shorter courses. 3. Adequate number of fit persons available to assist with search at end of event if required (see also provisions relating to a search for a lost competitor). |  |
| Nature of risk | Likeli-hood | Serious- ness | Risk control measures | Check |
| C. Risks to outside parties Collisions with members of the public | 1 | 2 | 1. Set courses to avoid use of popular walking paths, milling areas etc. 2. Warnings issued to competitors (verbal/written). |  |
| Conflict with public access/ movement (e.g. along cyclepaths, walking paths) | 1 | 2 | 1. Locate assembly areas, tents, parking etc. away from paths. |  |
| Traffic accidents at assembly area | 2 | 2 | 1. Avoid hazardous areas for car parking. 2. Develop traffic management plan in consultation with Roads ACT to manage safe entrance and exit for event area. 3. If appropriate, advise competitors of traffic arrangements. |  |
| Interference/nuisance at residences (e.g. farmhouses) from traffic or competitors | 1 | 2 | 1. Set courses to keep well away from residences. 2. Avoid routing traffic past residences or erect ‘Slow Down’ signs. 3. Liaise with residents with respect to traffic and course arrangements if appropriate. |  |
| Conflict with other events/ public uses | 2 | 2 | 1. Confirm no likelihood of conflict with landholder/ manager. 2. Contact other known regular users of area if necessary. 3. Avoid exclusive occupancy of public picnic areas/ car parks for assembly area. 4. For Day 1, develop communication plan to alert potential park visitors the nature of the event. |  |
| Degradation of area due to litter and waste products | 2 | 3 | 1. Provide portable toilets (1 per 100 competitors). 2. Provide rubbish bins in the assembly area. 3. Ensure the area is clean on completion of event. |  |
| Damage to fences | 1 | 2 | 1. Advise competitors to report any damage to fences. 2. Organisers to inspect potential damage areas after event. 3. Locate stiles etc. at heavily used fence crossings. 4. Identify compulsory routes to channel competitors through gates or stiles where appropriate. |  |
| Damage to underground services (e.g. irrigation systems, cables) caused by tent pegs, control stands etc. | 1 | 3 | 1. Locate tents, control stands etc. in non-irrigated areas or where there are no apparent services. 2. Consult with management staff if in doubt. |  |
| Damage to environmentally sensitive sites, cultivated areas, rehabilitation areas etc. | 2 | 2 | 1. Provide course planners with information about known sensitive sites as advised by relevant authorities. 2. Plan courses to avoid controls or obvious route choices within sensitive sites. 3. If appropriate, mark sensitive sites out of bounds on map and through tapes in terrain. 4. For Day 1, control sites not to be placed within 20m of significant sites identified by Namadgi. Note: See Orienteering Australia environmental guidelines for further information. |  |
| Injury to wildlife, particularly kangaroos | 2 | 3 | 1. Plan courses to send all competitors in the same direction. 2. If practicable, keep some areas free of competitors so that they can function as wildlife refuge areas. 3. Dogs not permitted at orienteering events. |  |

| Nature of risk | Likeli-hood | Serious- ness | Risk control measures | Check |
| --- | --- | --- | --- | --- |
| Injury/damage to livestock | 1 | 3 | 1. Set courses to avoid areas currently used by livestock. 2. If appropriate, negotiate with landholders to relocate livestock during event. 3. Advise competitors to avoid disturbing livestock. 4. Dogs not permitted at orienteering events. |  |
| Vandalism or other interference to property by children | 2 | 3 | 1. Sensitive areas (e.g. old buildings, machinery) signposted out of bounds. 2. Advice to parents to keep children away from sensitive areas. |  |

## Further References

- Competition Rules for Orienteering Australian Foot Orienteering Events in particular

  - Appendix 2 : Principles for Course Planning

  - Appendix 4 : Health and Safety Guidelines

  - Appendix 7 : Environmental Code of Practice

- OACT : Guidelines for Event Management – Doc 6

- Orienteering Australia: Risk Management (see OA Operational Manual 4.8)

For further information on orienteering refer to -

http://www.act.orienteering.asn.au/			http://www.orienteering.asn.au/

## Emergency Contact Numbers and Helicopter Landing Reference

| Emergency 000 or 112 ACT Ambulance Service (02) 6207 9980 Canberra Hospital (02) 6244 2222 Calvary Hospital (02) 6201 6111 Queanbeyan Hospital (02) 6298 9211 Cooma Hospital (02) 6455 3222 Cooma Police Station (02) 6242 0099 SES 13 2500 | Rural Fire Service (NSW) 1800 679 737 Monaro Office (02) 6456 4555 OACT Sat Phone 0147 140 690 Bob Mouatt 0429 398 794 Bob Allison 0408 407 141 Bill Jones 0428 255 210 Craig Mitchell at Gaerloch (02) 6453 3388 Helicopter Landing Reference -36° 11' 59.24", +149° 28' 56.54" |
| --- | --- |

Prepared by:

Robert Mouatt

###### Name

Manager Major Events, Orienteering ACT

###### Position

…………………………………………….…….

###### Signature

30 May 2011

###### Date